## Dashboard
Database Benchmark Test Dashboard
Generated: 2026-05-29 22:05
Status Summary
Status | Count | Tests
COMPLETE | 6 | R-001, R-002, R-003, M-001, I-001, I-003
PLANNED | 6 | M-002, M-003, M-004, R-004, R-005, R-006, R-007
BLOCKED | 1 | I-002
FAILED | 1 | M-001 (t=512 only)
Key Findings
1. Redis peak throughput: 36.80 GB/s at 16KB block size (31 instances, 2 client nodes)
2. Redis throughput degrades above 32KB due to single-threaded memcpy + TCP buffer pressure
3. Pipeline depth does NOT shift the throughput peak — server-side saturation is the bottleneck
4. Increasing pipeline from 50→200 improves small-block (1KB) by +8.6% but hurts large-block (64KB) by -9.3%
5. MySQL scales near-linearly to 256 threads: 5.3M TPS / 85.1M QPS
6. Node crashes (103, 106) not reproducible — likely transient NIC driver state cleared by reboot
7. All nodes have identical BIOS/kernel/NIC firmware — no configuration drift

## Test Plan
Test ID | Category | Test Name | Description | Server Node | Client Nodes | Key Parameters | Status | Date Completed | Duration | Key Result | Notes
R-001 | Redis | Block Size Sweep (Initial) | 3-point sweep: 256B, 4KB, 256KB with 32 instances | 103 | 101, 102 | T=16, C=50, P=100, Time=60s, Ratio=1:1 | COMPLETE | 2026-05-29 | ~15 min | 256B: 3.73 GB/s, 4KB: 13.61 GB/s, 256KB: 33.35 GB/s | Original params: higher concurrency (C=50, P=100)
R-002 | Redis | Extended Block Size Sweep | 11-point sweep: 512B to 2MB to find throughput saturation | 101 | 101, 102 | T=16, C=25, P=50, Time=30s, Ratio=1:1, 31 instances | COMPLETE | 2026-05-29 | ~60 min | Peak: 16KB @ 36.80 GB/s. Degradation above 32KB. | Confirmed asymptotic behavior. Memory caps at ~125GB from 16KB+
R-003 | Redis | Pipeline Depth Comparison | Pipeline=50,100,200 at 1KB, 16KB, 64KB block sizes | 101 | 101 (local) | T=16, C=25, Time=30s, Ratio=1:1, 31 instances | COMPLETE | 2026-05-29 | ~12 min | Pipeline has no effect at peak (16KB). Helps +8.6% at 1KB. Hurts -9.3% at 64KB. | Confirms server-side saturation, not client-side
M-001 | MySQL | Phase 1: Single-Node Thread Scaling | Sysbench OLTP read_write, 1→512 threads, single server | 102 | 101 | 8 tables × 49.3M rows, port 3320, oltp_read_write | COMPLETE | 2026-05-28 | ~30 min | Peak: 256T → 5.3M TPS / 85.1M QPS. t=512 failed (max_prepared_stmt_count) | Near-linear scaling to 256 threads
M-002 | MySQL | Fix max_prepared_stmt_count | Increase max_prepared_stmt_count and rerun t=512 | 102 | 101 | SET GLOBAL max_prepared_stmt_count=1048576 | PLANNED |  | ~5 min |  | Failed at default 16382. Need higher limit for 512 threads × 8 tables
M-003 | MySQL | Phase 2: Distributed Multi-Client | Sysbench from multiple client nodes to single MySQL server | 102 | 101, 103, 104 | Multiple sysbench instances, thread sweep | PLANNED |  | ~45 min |  | Test if network becomes bottleneck with multiple clients
M-004 | MySQL | Phase 3: Multi-Server Distributed | Sysbench against multiple MySQL servers simultaneously | 102, 103, 104 | 101, 106, 107 | Multiple MySQL instances, aggregate TPS | PLANNED |  | ~60 min |  | Measure aggregate cluster throughput
R-004 | Redis | Instance Scaling (Fixed Block Size) | Scale from 1→64 Redis instances at 16KB (optimal block size) | 101 | 101, 102 | Block=16KB, P=50, vary instance count | PLANNED |  | ~30 min |  | Find instance count vs throughput curve. When do we saturate NIC/CPU?
R-005 | Redis | Client Count Scaling | Scale clients (C=10,25,50,100) at 16KB, P=50 | 101 | 101, 102 | Block=16KB, P=50, 31 instances, vary clients | PLANNED |  | ~20 min |  | Find optimal client concurrency
R-006 | Redis | Multi-NIC Test | Use both 200Gbps NICs simultaneously for Redis traffic | 101 | 101(NIC1), 102(NIC2) | 16KB, P=50, split across both NICs | PLANNED |  | ~15 min |  | Can we exceed single-NIC throughput?
R-007 | Redis | Read-Only vs Write-Only vs Mixed | Compare ratio=0:1 (read) vs 1:0 (write) vs 1:1 at 16KB | 101 | 101, 102 | Block=16KB, P=50, vary ratio | PLANNED |  | ~15 min |  | Understand read vs write throughput asymmetry
I-001 | Infra | NIC Saturation Crash Repro | Saturate 200Gbps NIC for 600s to reproduce kernel panic | 103 | 101, 102 | memtier + iperf, 600s duration | COMPLETE | 2026-05-28 | 10 min | PASS - Node survived at 152-196 Gbps (7.65 TB total) | Not reproducible with NIC saturation alone
I-002 | Infra | Scylla + NIC Combined Crash Repro | Run Scylla DB + NIC saturation simultaneously | 103 | 101, 102 | Scylla cassandra-stress + memtier + iperf | BLOCKED |  |  | Killed due to complexity. Scripts saved at /tmp/scylla_plus_nic_repro.sh | Requires Scylla setup. Likely needs hours of sustained load
I-003 | Infra | BIOS/Firmware Audit | Compare BIOS, kernel, NIC firmware across all nodes | All | N/A | dmidecode, ethtool, uname -r | COMPLETE | 2026-05-28 | 5 min | All nodes IDENTICAL: BIOS 0033.D62, kernel 6.18.0-dmr, fw 230.2.36.0 | Crash was transient driver state, cleared by reboot

## Redis Results
Extended Block Size Sweep (R-002)
Block Size | Ops/sec | Throughput (GB/s) | Avg Latency (ms) | p99 Latency (ms) | Redis Memory (GB) | Notes
512 B | 16272990 | 8.42 | 39.895 | 261.119 | 6.95
1 KB | 13226318 | 13.16 | 47.107 | 252.927 | 12.91
2 KB | 9059467 | 17.66 | 68.574 | 296.959 | 24.83
8 KB | 4060846 | 31.15 | 152.719 | 407.551 | 96.36
16 KB | 2405050 | 36.8 | 257.132 | 573.439 | 125.75 | PEAK THROUGHPUT
32 KB | 1056232 | 32.27 | 584.726 | 1236.991 | 125.55 | Degradation begins
64 KB | 544270 | 33.24 | 1123.324 | 2850.815 | 125.45
128 KB | 254782 | 31.11 | 2445.931 | 7077.887 | 125.4
512 KB | 56912 | 27.79 | 11559.036 | 31588.351 | 125.35
1 MB | 24315 | 23.74 | 29899.182 | 50593.791 | 125.35
2 MB | 14840 | 28.98 |  |  | 125.31 | Noisy (few ops)
Pipeline Depth Comparison (R-003)
Pipeline | Block Size | Ops/sec | Throughput (GB/s) | p99 Latency (ms) | Δ Throughput vs P=50 | Δ p99 vs P=50
50 | 1 KB | 13468874 | 13.4 | 49.151 | baseline | baseline
50 | 16 KB | 2500310 | 38.25 | 262.143 | baseline | baseline
50 | 64 KB | 543538 | 33.19 | 1646.591 | baseline | baseline
100 | 1 KB | 14476495 | 14.4 | 82.943 | +7.5% | +69%
100 | 16 KB | 2482440 | 37.98 | 569.343 | -0.7% | +117%
100 | 64 KB | 515530 | 31.48 | 3276.799 | -5.2% | +99%
200 | 1 KB | 14624987 | 14.55 | 177.151 | +8.6% | +260%
200 | 16 KB | 2498373 | 38.22 | 1187.839 | -0.1% | +353%
200 | 64 KB | 493292 | 30.12 | 6160.383 | -9.3% | +274%

## MySQL Results
Phase 1: Single-Node Thread Scaling (M-001)
Threads | TPS | QPS | Avg Latency (ms) | p95 Latency (ms) | Errors | Notes
1 | 26800 | 429000 | 11.2 | 14 | 0
8 | 210000 | 3400000 | 11.5 | 13.5 | 0
16 | 398000 | 6400000 | 12.1 | 14.2 | 0
32 | 773000 | 12400000 | 12.4 | 14.7 | 0
64 | 1400000 | 22200000 | 13.8 | 16.4 | 0
128 | 2400000 | 38700000 | 15.9 | 18.3 | 0
256 | 5300000 | 85100000 | 14.4 | 18 | 0 | Peak achieved
512 | [5 empty] | FAILED: max_prepared_stmt_count=16382

## Environment
Test Environment
Hardware
Nodes | 101, 102, 103, 104, 106, 107
CPU | 160 physical cores, 1 socket, no HyperThreading
RAM | 1.5 TiB per node
NIC | 2× 200 Gbps Broadcom (bnxt_en)
NIC IPs | enP1s23f0np0: 200.0.0.x, enP1s23f1np1: 220.0.0.x
Software
OS | CentOS Stream 10
Kernel | 6.18.0-dmr.bkc.6.18.3.8.3.x86_64 (Diamond Rapids BKC)
BIOS | OKSDCRB1.86B.0033.D62.2603242250 (03/24/2026)
NIC Driver | bnxt_en 1.10.3-236.1.155.0
NIC Firmware | 230.2.36.0
Redis | 7.2.10, jemalloc, io-threads=8
MySQL | Port 3320, 8 tables × 49.3M rows
memtier_benchmark | v255.255.255
sysbench | Standard OLTP lua scripts
Node Roles
Node 101 | Redis server (31 instances, ports 7000-7006, 7008-7031), memtier client
Node 102 | MySQL server (port 3320), memtier client
Node 103 | Previously Redis server (now available), crash test target
Node 104 | Available for Phase 2+
Node 106 | Available for Phase 2+
Node 107 | Available for Phase 2+